- Annex V: WORK PLAN

- Hydraulic automatic continuous press

- Based on Article 13 of the Special Conditions, the table will be filled in by the Contracting Authority and sent to the contractor together with the Commencement Order. The Contractor shall countersign it and return it within 15 days to the Contracting Authority. The Contractor will adhere to the time limits set therein.

| Activity | Deadlines (requirement as per contract, in calendar days) | Period - cumulated number of days (to be filed by the tenderer) | Dates (to be filled in by the Contracting Authority) |
| --- | --- | --- | --- |
| Commencement order (S.C., Article 18) | After signature of the contract by both parties | NA | 21.08.2019 |
| Detailed Implementation Plan (S.C., Article 13) | 5 days after signing of the contract | NA | 26.08.2019 |
| - I. Procurement of Hydraulic automatic continuous press |  |  |  |
| Hydraulic automatic continuous press | To be specified by the tenderer |  | [DD/MM/YY](*) |
| Hydraulic upgrade | To be specified by the tenderer |  | [DD/MM/YY] |
| Mandatory support and maintenance - Technical support and maintenance of the entire equipment | To be specified by the tenderer |  | [DD/MM/YY] |
| Verification Operations: (Annex II: Technical Specifications) - User manuals; - Testing of the vehicle and hydraulic upgrade. | After the complete system is operational Max. 90 days |  | 26.11.2019 |
| Submission of administrative and technical manuals and Post-completion documentation | With the request for Provisional Acceptance |  | 26.11.2019 |
| Request for Provisional Acceptance (G.C., Article 31) | After completion of the task/procurement (including trainng) |  | 05.12.2019(*) |
| Provisional Acceptance (G.C., Article 31) | Maximum 10 days after the request from the contractor |  | 26.11.2019(*) |
| End of Warranty (S.C., Article 32) | PA + 2 years |  | 26.11.2021(*) |
| Final Acceptance (G.C., Article 34) | PA + 3 years after the Provisional Acceptance |  | 26.11.2022 (*) |
| Release of the Performance guarantee (GC, Article 11) | After the end of the Warranty period |  | 26.11.2021 (**) |

(*) To be communicated by the Contracting Authority based on the actual date of the Provisional Acceptance

(**) Performance guarantee shall be released within 30 days of the actual date of the Final Acceptance

NOTE: All deadlines except the end of warranty period and end of after-sales services are final deadlines on which relevant activity must be executed, meaning that activities can be executed earlier which will be reflected in the updated Programme of implementation of tasks. Only the warranty shall remain valid for exactly three years after the provisional acceptance as stipulated in Article 32 of the Special Conditions.

The deadline set here is the final deadline, set by the Contracting Authority, when all verification operations must be executed in order to finish the implementation in accordance with the contract. Distribution of days for each activity within the verification operations shall be agreed with the Contractor.